Every task, its owner, and whether it is done

Nidan — Build Status

Nidan — Bias-Aware Virtual Patient Simulator

Authors       Vraj Patel (202301408) · Yogesh Bagotia (202301114)

Mentor        Abhishek Gupta

Institution   DAU (Dhirubhai Ambani University), Gandhinagar

Status        Generated

Part of       Build log

# Contents

| Generated | 2026-09-12 — python scripts/build_status.py |
| --- | --- |
| Source | docs/spec/BUILD_PLAN.md (do not edit this file by hand) |
| Tasks complete | 8 of 34 (24%) |
| Effort | 11 d done · 72 d remaining |
| Branch | docs/decide-d4-d7 |
| Last commit | 96a795c feat(db): schema and migrations (T-010) |

Estimates are engineering effort only. They do not include the clinical content authoring that BUILD_PLAN §11.1 rates the real critical path — see the last section.

## Phases at a glance

| Phase | Tasks | Done | Effort left | Status |
| --- | --- | --- | --- | --- |
| Phase 0 — Foundation | 7 | 7 | 0 d | ✅ complete |
| Phase 1 — Persistence and accounts | 9 | 1 | 15 d | 🟡 in progress |
| Phase 2 — Admin console P0 | 4 | 0 | 12 d | ⬜ not started |
| Phase 3 — API and web app | 8 | 0 | 28 d | ⬜ not started |
| Phase 4 — Commercial readiness | 6 | 0 | 17 d | ⬜ not started |

## Phase 0 — Foundation

7 of 7 complete

|  | Task | Owner | Est | Depends | Build log |
| --- | --- | --- | --- | --- | --- |
| ✅ | T-001 · Restructure into a nidan/ package | Vraj | 2 d | — | T-001 |
| ✅ | T-002 · Test harness and fake LLM gateway | Vraj | 2 d | T-001 | T-002 |
| ✅ | T-003 · Lexicon disjointness test ⭐ | Vraj | 0.5 d | T-002 | T-003 |
| ✅ | T-004 · CI pipeline with the validation gate ⭐ | Vraj | 1 d | T-002 | T-004 |
| ✅ | T-005 · Docker + docker-compose | Vraj | 1 d | T-001 | T-005 |
| ✅ | T-006 · Typed configuration | Vraj | 1 d | T-001 | T-006 |
| ✅ | T-007 · Structured logging and Sentry | Vraj | 0.5 d | T-006 | T-007 |

## Phase 1 — Persistence and accounts

1 of 9 complete

|  | Task | Owner | Est | Depends | Build log |
| --- | --- | --- | --- | --- | --- |
| ✅ | T-010 · Schema and migrations | Vraj | 3 d | T-005 | T-010 |
| ⬜ | T-011 · Seed content and openapi.yaml skeleton ⭐ | Vraj | 2 d | T-010 | — |
| ⬜ | T-012 · Repository layer and tenant scoping | Vraj | 2 d | T-010 | — |
| ⬜ | T-013 · Event-sourced session state ⭐ | Vraj | 3 d | T-012 | — |
| ⬜ | T-014 · Supabase Auth integration | Vraj | 2 d | T-012 | — |
| ⬜ | T-015 · Anonymous trial sessions | Vraj | 1.5 d | T-013,T-014 | — |
| ⬜ | T-016 · Assessment from events ⭐ | Vraj | 2 d | T-013 | — |
| ⬜ | T-017 · Free-tier allowance and case selection | Vraj | 1.5 d | T-014 | — |
| ⬜ | T-018 · Pilot data backfill | Vraj | 1 d | T-016 | — |

## Phase 2 — Admin console P0

0 of 4 complete

|  | Task | Owner | Est | Depends | Build log |
| --- | --- | --- | --- | --- | --- |
| ⬜ | T-020 · Admin shell and auth | Yogesh | 1 d | T-014 | — |
| ⬜ | T-021 · Case editor ⭐ | Yogesh | 5 d | T-020,T-011 | — |
| ⬜ | T-022 · Playtest with live instrumentation ⭐ | Yogesh | 4 d | T-021,T-016 | — |
| ⬜ | T-023 · Clinical review workflow ⭐ | Yogesh | 2 d | T-022 | — |

## Phase 3 — API and web app

0 of 8 complete

|  | Task | Owner | Est | Depends | Build log |
| --- | --- | --- | --- | --- | --- |
| ⬜ | T-030 · JSON API ⭐ | Vraj | 6 d | T-016,T-017 | — |
| ⬜ | T-031 · LLM gateway hardening | Vraj | 2 d | T-006 | — |
| ⬜ | T-032 · Next.js scaffold and auth | Yogesh | 4 d | T-011 | — |
| ⬜ | T-033 · Dashboard and onboarding | Yogesh | 3 d | T-032 | — |
| ⬜ | T-034 · Consultation screen ⭐ | Yogesh | 6 d | T-030,T-032 | — |
| ⬜ | T-035 · Real-patient-data guard | Vraj | 1 d | T-034 | — |
| ⬜ | T-036 · Feedback screen ⭐ | Yogesh | 3 d | T-030,T-032 | — |
| ⬜ | T-037 · History and progress | Yogesh | 3 d | T-036 | — |

## Phase 4 — Commercial readiness

0 of 6 complete

|  | Task | Owner | Est | Depends | Build log |
| --- | --- | --- | --- | --- | --- |
| ⬜ | T-040 · Leakage monitor ⭐ | Vraj | 3 d | T-030 | — |
| ⬜ | T-041 · Stripe subscriptions | Vraj | 4 d | T-030 | — |
| ⬜ | T-042 · Pricing and account screens | Yogesh | 3 d | T-041,T-032 | — |
| ⬜ | T-043 · AI usage and cost dashboard | Yogesh | 2 d | T-031,T-020 | — |
| ⬜ | T-044 · Master list and lexicon editors | Yogesh | 3 d | T-020 | — |
| ⬜ | T-045 · Launch readiness | Both | 2 d | all above | — |

⭐ marks a task the plan flags as load-bearing — it protects a property in CLAUDE.md, unblocks another track, or closes a known risk.

A task shows ✅ only when its BUILD_PLAN entry carries a DONE marker. Every completed task has a build log recording what was actually built, where it diverged from the specification, and what debt it left.

Phases 5–7 are not listed. BUILD_PLAN §9 summarises them as prose rather than itemised tasks — measurement upgrade (11 d), mobile (20 d) and Case Factory (22 d) — and they are expanded when the phase begins. The counts above therefore cover the work through launch, which is what there is to track today.

## The thing this table cannot show

Every number above is engineering effort. Ten clinically reviewed cases gate launch and five exist. No task in this plan produces one: writing a case is clinical authoring, not development, and it needs no developer time.

The two clinician reviewers cannot start until T-021 (case editor) and T-023 (review workflow) exist, because until then only a programmer can read a case. That is 12 days of Phase 2 work away, and authoring the drafts can begin before it.

BUILD_PLAN §11.1 rates this the risk to the schedule, and it is the one a task tracker makes easy to forget — because it has no task.